TT Brooklyn MEETING: MINUTES and ACTION POINTS

STEERING Group Meeting

Date of meeting: 13/01/2010   Location: Penthouse   Time: 6pm

Individuals present: Belinda, Barb, Spencer

Apologies from: Hina

Chair/Minute Taker: Belinda

AGENDA (Refer to previous meeting’s minutes and/or fill in at beginning of meeting):

Picnic for the planet – stall

Template for minutes

Calendar for 2010

Aims and Objectives for 2010

Updates from other groups

Finances

ACTION POINTS FROM LAST MEETING COMPLETED?

No actions from previous meetings outstanding

ACTION POINTS (Note down action points as they occur during meeting)

For each action point please note who is responsible for its completion, by when and what resources/support is needed to do so.

1. Picnic

Belinda explained that we were organising a stall on behalf of Wellington TT and that we would need volunteers to help staff the stall. Ideas for the stall were that we would have a limited amount of information on the stall with the intention of engaging people in conversations about TT. We would create some kind of “wishing line” where we would invite people to write their hopes for their community/the planet. We would also have a map of the Wellington region where people could put stickers of where they are from if they are in a TT group or in another colour if they are interested in the movement. Sign up sheets for the different local TT groups would be made available. The picnic runs from 11-4, set-up time is from 10 to 10.45am and packup is from 4-5pm

Actions

- Belinda: to check times and circulate along with rota to volunteers, and request for baking, get something to use as labels for wishing line, create sign-up sheets, bring TT flyers.

- Barb to bring Posters and materials to make Wishing Line (bamboo poles and string) also to see if she has two colours of sticky dots at home.

- Spencer to bring a blanket with TT on it  and to get big map and markers (in the absence of sticky dots)

2.  Minutes template

- Belinda forgot to bring it but said she would type minutes in to it and see if it worked. Then post them on the wikki

3. Calendar for 2010

Spencer suggested it would be a good idea if we could plan the agenda for the whole year so that we knew what was coming up. Belinda reflected that Anne (from the food group) had thought that a public meeting and a steering group meeting each month was probably a bit ambitious for the steering group. Discussion followed about the possibility of rotating the public meeting slot round the sub groups so they could showcase a particular issue and also keep it fixed in peoples minds that TT Brooklyn held public meetings on the fourth wed every month.

- Barb to book community centre

- Belinda to contact food group to see if they are interested

- Spencer to communicate the idea to the waste group.

- Barb to check in with Ron Eckman about the January meeting (if Ron available we will be doing something on change, if not we thought it could be an opportunity to find out what people wanted TT Brooklyn to focus on in the next 12 months.

4. Aims and objectives for 2010

Spencer thought it would be good for the sterring group to have some aims for the next 12 months. Everyone agreed. To be discussed at the next steering group meeting.

5. Updates from other group, Spencer gave a brief update from the Waste Minimisation group.

6. Finances, Barb suggested that we keep an eye out for ways to increase funds for the steering group. All agreed

Tentative agenda for next meeting: _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ __ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ Date, location and time of next meeting: As circulated previously._ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _